Study Plan to Paper 1 Publication

Edmond Mwinbamon Balika | BCEPS / IGS, University of Bergen | Target: Paper 1 Submission - months 12–15

1. Phased Study Plan (Months 1–15)

| Phase | Learning Focus | Resources | Study Actions & Deliverable | UiB Foundational Coursework |
| --- | --- | --- | --- | --- |
| Months 1–3 Epidemiology & Disease burden | How incidence, prevalence, mortality; DALY / YLL / YLD are derived at sub-national level as per GBD logic; descriptive vs causal claims | A: GBD 2023 Diseases & Injuries; Causes of Death; Risk Factors A: WHO Global Health Estimates A: Intro epidemiology text/course | • Health Metrics Notebook (defs, equations, Ghana examples) • Worked DALY examples Deliverable: can explain and interpret GBD outputs | • Complete personal-data e-course (Mitt UiB) • Enrol MEDMET901 Ethics & health research (7 ECTS; aim Year 1) • Join CIH–CISMAC / IGS research school • Confirm elective plan with supervisors (≤30 ECTS total) |
| Months 2–5 GIS fundamentals | Vector/raster, CRS, joins, clipping, reprojection; Ghana admin units; proximity vs travel time vs effective access | B: QGIS Training Manual B: A Gentle Introduction to GIS E: Ghana 2021 PHC; DHS 2022; GHS/MoH facility docs | • QGIS drills on Ghana boundaries, WorldPop, roads, facilities • Clean region/district map project Deliverable: reproducible Ghana spatial project (QGIS) | • MEDMET901 sessions / home exam as scheduled • Research-school seminars (global health / methods) • Begin logging dissemination hours toward FORMIDL901 |
| Months 4–7 R spatial & reproducibility | sf, terra, ggplot2, exactextractr; zonal stats; spatial allocation; Git + project structure | B: R spatial docs (sf, terra, ggplot2, exactextractr) E: WorldPop; census; admin layers; DHIS2 (if accessible) | • Scripted Ghana spatial database • Join population ↔ admin units • Version-controlled paper1/ pipeline Deliverable: sf/terra workflow joining population & admin data | • Keep coursework bounded: protect 15–18 h/week research time • Align any methods electives with GIS/epi gaps (supervisor OK) |
| Months 5–9 Access, inequality, uncertainty | Friction surfaces; dry/rain travel time; concentration index, SII/RII, Theil; uncertainty in the pipeline | B: Spatial accessibility literature (travel time / access) E: OSM roads; friction/seasonal layers; DHS stratifiers A: revisit GBD uncertainty concepts as needed | • Pilot accessibility metric (1 region/districts) • One inequality measure + short interpretation note • Uncertainty hooks in code (not end add-on) Deliverable: working Paper 1 pilot + reproducible pipeline | • Research-school presentations / internal talks (dissemination credits) • Mid-way evaluation planning only if timing falls in window |
| Months 9–15 Paper 1 production | Freeze core RQ & analysis plan; scale pilot nationally; validation; package method; draft & submit | A + B + E as needed for methods/results write-up Writing: applied spatial-burden papers as models Defer deep C & D (costing / CEA) until Paper 2–3 | • National core analysis + validation + uncertainty • R package / reproducible method • Manuscript draft early; iterate with supervisors Deliverable: Paper 1 submitted (~ mo. 12–15) | • Use Paper 1 seminar/conference abstract toward dissemination ECTS • Do not stack new heavy electives during write-up |

2. Resource Priority for Paper 1

| Block | Priority to Paper 1 | Usage |
| --- | --- | --- |
| A. Epidemiology & disease burden | Essential | Core reading path for Months 1–3 and GBD interpretation throughout Paper 1 |
| B. GIS & spatial health | Essential | QGIS → R spatial → accessibility literature in sequence above |
| E. FairChoices & Ghana evidence | Essential (Ghana data) | Census, DHS, GHS/MoH, DHIS2 for spatial layers & validation; FairChoices depth can wait for Paper 3 |
| C. Health economics & costing | Defer | Light awareness only; start after Paper 1 submission |
| D. Equity, CEA | Defer | Conceptual skim optional; deep study in Year 2–3 for Paper 3 |

3. Progress Checkpoints

| By | Must be true | Evidence |
| --- | --- | --- |
| Month 3 | Explain epidemiologic/burden measures disaggregation; interpret GBD outputs | Health Metrics Notebook + short oral/written check with supervisor |
| Month 6 | Acquire, clean, join and map principal Ghana spatial datasets | Scripted maps + README in gis/ / data/ |
| Month 9 | Working Paper 1 pilot + reproducible analysis pipeline | Pilot repo run that regenerates key figures |
| Month 12–15 | Paper 1 submitted | Submission confirmation + deposited preprint/supplement if used |

4. Weekly Blocks During UiB Course Weeks

| Activity | Normal Week | Heavy Course Week (e.g. MEDMET901) |
| --- | --- | --- |
| Research / Data Analysis | 15–18 h | 8–10 h |
| Reading (A/B/E) | 5 h | 3 h (course reading counts toward A where overlapping) |
| GIS / Spatial Practice | 4 h | 2 h |
| UiB Courses / BCEPS Research | 2–4 h | 15–20 h (block weeks) |
| Academic writing | 4 h | 2 h |
| Supervision | 1–2 h | 1 h |